## Folha1
Task |  | Start Date | End date | Done by | Status
Phase 1
1.1 -Project creation | 1.1.1 - Repository creation | 2022-10-18 | 2022-10-19 | Martim Costa 64901, Ana Gadelha 59943 | Done
| 1.1.2 - Identify code smells | 2022-10-19 | 2022-10-21 | All | Done
| 1.1.3 - Identify GoF design patterns | 2022-10-20 | 2022-10-21 | All | Done
| 1.1.4 - Review each others work | 2022-10-21 | 2022-10-22 | All | Done
| 1.1.5 - Make report | 2022-10-21 | 2022-10-22 | All | Done
Phase 2
2.1 - New functionalities | 2.1.1 - Brain storm 2 new functionalities | 2022-11-07 | 2022-11-08 | All | Done
| 2.1.2 - Come up with the user stories | 2022-11-08 | 2022-11-09 | All | Done
| 2.1.3 - Write the report | 2022-11-09 | 2022-11-09 | Martim Costa 64901, Pedro Arruda 60663 | Done
| 2.1.4 - Problem fixing | 2022-11-23 | 2022-11-25 | All | Done
| 2.1.5 - Brain storm on implementation | 2022-11-23 | 2022-11-27 | All | Done
| 2.1.6 - Study and analyze of the code | 2022-11-28 | 2022-11-29 | All | Done
| 2.1.7 - Start of the implementation of the new functionalities | 2022-11-28 | 2022-11-30 | All | Done
| 2.1.8 - Implementation of the functionalities | 2022-12-01 | 2022-12-04 | All | Done
2.2 - Metrics | 2.2.1 - Metrics analyses | 2022-11-28 | 2022-12-01 | All | In Progress
| 2.2.2 - Review metrics of each others | 2022-11-28 | 2022-12-01 | All | In Progress
2.3 - Use Cases | 2.3.1 - Use case diagrams | 2022-12-01 | 2022-12-02 | All | Done
| 2.3.2 - Use cases description | 2022-12-01 | 2022-12-02 | All | Done
| 2.3.3 - Use cases reviews | 2022-12-01 | 2022-12-04 | All | Done
2.4 - Tests | 2.4.1 - Unit tests | 2022-12-01 | 2022-12-04 | All | Done