## Folha1
TODO | In Progress | Review | Done | Done By
Phase 1 - Sprint 1
Preparing the workplace |  |  | X | Martim Costa 64901
Identify 3 code smells(15 total) |  |  | X | All
Identify 3 GoF design patterns(15 total) |  |  | X | All
Review each others work |  |  | X | All
Make the report |  |  | X | All
Phase 2 - Sprint 1
Brain storm 2 new functionalities |  |  | X | All
Come up with the respective user stories |  |  | X | All
Write the report |  |  | X | Martim C., Pedro A.
Phase 2 - Sprint 2
General program problem fixing |  |  | X | All
Group Thinking on how to implement new functionalities |  |  | X | All
Phase 2 - Sprint 3
Study and analyze of the code |  |  | X | All
Start of the implementation of the new functionalities |  |  | X | All
Metrics analyses | X |  |  | All
Review metrics of each others | X |  |  | All
Phase 2 - Sprint 4
Use case diagrams | X |  |  | All
Use cases description | X |  |  | All
Use cases reviews | X |  |  | All
Implementation of functionalities | X |  |  | All
Unit tests | X |  |  | All