## Burndown Chart
Sprint 1 Burndown Chart
Task ID | Task Description | Initial Estimate | 2022-11-07 | 2022-11-08 | 2022-11-09
|  | Day 0 | Day 1 | Day 2 | Day 3
1 | Brain storm new implementations | 2 | 1 | 1
2 | Come up with user stories | 2 |  | 1 | 1
3 | Write the report | 1 |  |  | 1
Completed Effort |  | 0 | 1 | 2 | 2
Remaining Effort |  | 5 | 4 | 2 | 0
Ideal Burndown |  | 5 | 3.3333 | 1.6667 | 0