## Folha1
Task ID | Task Description | Initial Estimate | 2022-12-01 | 2022-12-02 | 2022-12-03 | 2022-12-04
|  | Day 0 | Day 1 | Day 2 | Day 3 | Day 4
1 | Use case diagrams | 10 | 4 | 4 | 2
2 | Use cases description | 3 |  | 1 | 1 | 1
3 | Use cases reviews | 2 |  | 1 | 1
4 | Implementation of functionalities | 6 | 2 | 2 | 2
5 | Unit tests | 2 |  |  | 1 | 1
Completed Effort |  | 0 | 6 | 8 | 7 | 2
Remaining Effort |  | 23 | 17 | 9 | 2 | 0
Ideal Burndown |  | 23 | 17.25 | 11.5 | 5.75 | 0